SAHYOG INDUSTRIES

Digital Transformation Roadmap

2025 – 2026  |  Comprehensive Program Plan

Prepared by: Digital Transformation Lead Team

Confidential  |  Accredian Capstone Project

Table Of Contents

Executive Summary	4

1. Strategic Alignment & Assessment	5

1.1 Business Objectives	5

1.2 Key Stakeholders	5

1.3 Value Drivers	6

1.4 Digital Maturity Assessment	6

1.5 SWOT Analysis for Digital Initiatives	7

2. Customer & Market Strategy	9

2.1 Target Customer Segments	9

2.2 B2B Customer Journey Map	9

2.3 Value Proposition & Monetization Opportunities	10

3. Operating Model & People	11

3.1 Digital Operating Model	11

3.2 Key New Roles	12

3.3 Change Management Overview	12

3.4 Change Management Plan	13

3.5 Training Program & Skill Development	13

3.6 Skill Development Roadmap	14

4. Technology Architecture & Digital Stack	16

4.1 Strategic Technology Pillars	16

4.2 Five-Layer Technology Architecture	17

4.3 Prioritized Technology Use Cases	17

4.4 Data Privacy & Compliance Framework	18

5. Roadmap, Delivery & Agile Plan	19

5.1 12-Month Phased Roadmap	19

5.2 Detailed Gantt Chart – Workstream Delivery Schedule	19

5.2 Resource & Budget Estimate (Year 1)	21

6. Metrics, KPIs & ROI Analysis	23

6.1 KPI Map Tied to Business Goals	23

6.2 ROI & NPV Calculation (Year 1)	23

7. Risk, Security & Regulatory Framework	25

7.1 Risk Register	25

7.3 Contingency Milestones	26

7.4 Three-Layer Transformation Governance	26

8. Aha! Strategic Roadmap – Portfolio View	28

8.1 Program Vision & Strategic Goals	28

8.2 Aha! Initiative Roadmap by Release Theme	28

8.3 Backlog Management & Prioritization Rules	30

Appendix A: Maturity Level Descriptors	32

Appendix B: Key Assumptions & Data Sources	32

Appendix C: Participation Matrix	32

# Executive Summary

Sahyog Industries is a 45‑year‑old, mid‑sized Indian manufacturing firm specializing in industrial components and assemblies with a national distribution and export channel. The company has strong operational expertise, an established B2B customer base, and several legacy production facilities. Sahyog Industries now stand at a critical inflection point because of unprecedented challenges: evolving customer demands, supply chain disruptions, labor shortages, trade disruptions, increasing competition and growing demand for customized and lean manufacturing have created an urgent imperative for digital transformation.

Digital transformation is critical because it enables manufacturing industries like Sahyog to be more agile, reduce costs, improve product quality, and respond faster to market changes. Manufacturers that embrace digital transformation can:

- Increase resilience against global supply chain disruptions

- Enhance operational efficiency through real-time monitoring and predictive analytics

- Improve product quality and compliance with data-driven decision-making

- Meet customer demand for faster delivery, customization, and transparency

In a time where agility and innovation are essential to survival, digital transformation isn’t a luxury; it’s a necessity.

This document presents a comprehensive, implementable Digital Transformation Roadmap covering strategy, people, process, and technology, designed to make Sahyog digitally mature across operations, sales, and service within 12 months.

Program Ambition Transform Sahyog Industries from a digitally-emerging manufacturer (Maturity Level 2) to an integrated, data-driven, customer-centric enterprise (Maturity Level 4) within 24 months, delivering 20-25% operational efficiency gains, 15-20% revenue growth, and a positive ROI by Q4 of Year 1.

| Total Budget (Yr 1) | Projected ROI (Yr 2) | Key Technologies | Program Duration |
| --- | --- | --- | --- |
| Rs. 4.2 Cr | ~172% | IoT, AI/ML, ERP, CRM | 12 Months (4 Phases) |

# 1. Strategic Alignment & Assessment

## 1.1 Business Objectives

The digital transformation program aims to modernize Sahyog's operations, address external competitive pressures, and leverage the company's 45 years of domain expertise through five strategic objectives:

| Objective | Description | Expected Outcome |
| --- | --- | --- |
| Operational Efficiency | Streamline legacy production facilities through automation, IoT integration, and data analytics to reduce downtime, optimize resource utilization, and transition to lean manufacturing principles. | 20-30% reduction in downtime and production costs |
| Supply Chain Resilience | Implement digital tools like AI-driven forecasting, blockchain for traceability, and real-time monitoring to mitigate disruptions, ensure timely procurement, and build more agile supplier networks. | Lead times cut from weeks to days; 40% fewer disruptions |
| Customization & Flexibility | ERP and digital twin integration with CAD-CAM systems for on-demand, B2B-tailored production | 3x more custom SKUs supported; 15% higher average order value |
| Market Competitiveness | Leverage digital channels for better customer engagement, predictive maintenance services, and data insights to differentiate from competitors, strengthen export capabilities, and explore new revenue streams like after-sales digital services. Digital B2B portal, analytics-driven sales, and data-backed after-sales services | 15-20% revenue growth; strengthened export pipeline |
| Innovation & Sustainability | Integrate sustainable practices through digital monitoring of energy use and waste, while encouraging a culture of continuous improvement to sustain long-term growth in a competitive Indian manufacturing landscape. | 10% reduction in energy costs; ESG compliance readiness |

These objectives align with the Board's push to address competition, disruptions, and market demands, ultimately aiming for cost reduction, revenue growth, and risk management.

## 1.2 Key Stakeholders

Stakeholders in this digital transformation program encompass internal and external parties who influence or are impacted by the initiative. They can be categorized as follows:

| Stakeholder | Role / Interest | Engagement Strategy |
| --- | --- | --- |
| Board of Directors | Strategic oversight; ROI focus; program sponsor | Monthly KPI dashboards; quarterly steering reviews |
| CEO / COO / CFO | Program execution; budget authority; alignment | Weekly updates; Digital Steering Committee membership |
| Operations & Production Teams | Frontline users; workflow changes; new tool adoption | Hands-on training; change champions; feedback loops |
| IT & Digital Teams | Technology implementation; integration; security | Agile squads; technical workshops; vendor management |
| B2B Customers | Benefit from faster, more customized delivery | Portal pilot; feedback sessions; SLA commitments |
| Suppliers & Partners | Supply chain digitization; collaborative platforms | EDI/API integration; supplier portal onboarding |
| Distributors | Enhanced tracking and inventory management | Distributor portal training; SLA performance tracking |
| Regulators (DPDP / IT Act) | Compliance with India's data privacy regulations | Legal review; compliance audit; periodic reporting |

## 1.3 Value Drivers

Value drivers are the core elements that generate measurable benefits from the digital transformation, quantifying success in terms of financial, operational, and strategic outcomes. The core value drivers for Sahyog's digital transformation are:

- Cost Optimization:

Predictive maintenance (20-30% repair cost reduction), inventory management to minimize waste and to cut holding costs, and energy-efficient processes in legacy facilities.

- Revenue Growth:

Enabling customized products to capture premium pricing, expanding B2B relationships via digital portals, and tapping into export markets with faster turnaround times, potentially increasing sales by 15-25%. (estimated 15-25% revenue uplift)

- Risk Mitigation:

Building supply chain visibility to reduce disruption impacts (e.g., shortening lead times from weeks to days), enhancing data security, and compliance with DPDP Act, and ensuring compliance, which lowers potential losses from downtime or penalties.

- Customer Satisfaction:

Delivering lean, tailored solutions that meet demands for customization, leading to higher retention rates, repeat business, and positive referrals in the competitive industrial sector.

- Innovation & Agility:

Harnessing data analytics for informed decision-making, fostering R&D through digital simulations, and creating scalable processes that adapt to market changes, driving long-term competitive advantage.

- Sustainability & ESG:

Incorporating green technologies to reduce environmental footprint, appealing to eco-conscious B2B clients and enhancing the company's reputation as a forward-thinking Indian manufacturer.

## 1.4 Digital Maturity Assessment

The Digital Maturity Assessment evaluates Sahyog Industries’ current digital capabilities across business, operations, technology, and culture. It helps answer:

- Where Sahyog is today (Current State)

- Where Sahyog needs to be (Future State)

- What gaps exist

- What initiatives should be prioritized

This ensures transformation is strategic—not just technology-driven.

Sahyog's current digital maturity was assessed using a five-level framework across eight dimensions (refer Appendix-A for Digital Maturity Model Framework). The company currently operates at Level 2 (Emerging) overall, with critical gaps in data infrastructure, customer-facing digital tools, and advanced technology adoption.

| Dimension | Current Level | Target (12M) | Key Gap to Address |
| --- | --- | --- | --- |
| Business Strategy & Leadership | Level 2 | Level 4 | - Transformation is IT-led, not business-led - implement Digital-first business strategy |
| Manufacturing & Operations | Level 1-2 | Level 3-4 | - Manual processes. - paper-based shop floor; - no IoT integration for predictive maintenance |
| Supply Chain & Logistics | Level 2 | Level 4 | - No real-time visibility into supply chain; - purely reactive planning - digital supply chain platform |
| Customer & Sales Digitization | Level 1-2 | Level 3 | - No B2B portal; - manual order processing; no CRM system |
| Technology & IT Architecture | Level 2 | Level 4 | - Legacy systems; - minimal integration; - No cloud presence - cloud based ERP is required |
| Data, Analytics & Intelligence | Level 1 | Level 3 | - No data lake; - no analytics platform; - ad hoc reporting only - AI driven forecasting is required |
| Workforce & Digital Culture | Level 2 | Level 3 | - Low digital literacy. - change resistance expected across sites - automation adoption to be fast tracked |
| Governance, Security & Compliance | Level 2 | Level 4 | - No cybersecurity framework; - DPDP readiness is absent - Compliance automation |

## 1.5 SWOT Analysis for Digital Initiatives

The SWOT analysis below synthesizes Sahyog Industries’ internal capabilities and external environment as they relate to the digital transformation program. It informs the strategic sequencing of initiatives in the roadmap.

►  Read the four quadrants as two lenses: Internal (Strengths/Weaknesses) tells you what Sahyog can control; External (Opportunities/Threats) tells you what it must respond to. The roadmap is sequenced to amplify strengths, close weaknesses, capture opportunities, and mitigate threats simultaneously.

| 💪 STRENGTHS (Internal – Positive) | ⚠️ WEAKNESSES (Internal – Negative) |
| --- | --- |
| - 45 years of domain expertise; mature supplier & distributor relationships - Established B2B customer base with recurring demand patterns supporting CRM and demand forecasting adoption - Stable revenue base to fund phased digital investments without financial instability - Skilled technicians and engineers who can transition to digital-augmented operations with targeted training - National distribution and export channel enabling rapid rollout of supply chain digital platforms | - Legacy ERP/MES systems with limited integration; paper-based tracking increases data-entry errors - Low digital maturity; IT perceived as cost center, not strategic driver; no Chief Digital Officer - Siloed data across Finance, Production, and Procurement limits cross-functional analytics - Resistance to change among shopfloor and middle management; digital literacy gaps across workforce - Limited Agile delivery experience; project execution historically waterfall, slowing digital deployments |
| 🚀 OPPORTUNITIES (External – Positive) | ☠️ THREATS (External – Negative) |
| - India’s National Manufacturing Policy and PLI scheme provide incentives for technology upgrades in industrial sectors - Industry 4.0 adoption accelerating: 81% of manufacturers globally report that disruptions accelerate DX (Rockwell, 2025) - Growing B2B demand for digital self-service, real-time order visibility, and configurable products - Cloud, AI/ML, and IoT solutions are now cost-accessible for mid-market Indian manufacturers - Premium pricing opportunity for customized/lean manufacturing with faster turnaround capabilities | - Rising competition from digitally native Indian and global manufacturers offering faster, cheaper components - Supply chain disruptions (geopolitical tensions, raw material volatility) threaten delivery reliability - Cybersecurity risks rising manufacturing accounts for 21% of ransomware attacks globally (Black Kite, 2025) - India’s DPDP Act (2023) and evolving IT compliance requirements add regulatory cost and complexity - Talent scarcity: skilled AI, IoT, and digital operations professionals are scarce in Tier-2/3 Indian cities |

# 2. Customer & Market Strategy

For Sahyog industries, Digital transformation should enhance, rather than disrupt, the relationship with the customer, leading to higher engagement and ROI. Customer and market strategy in a digital transformation (DT) roadmap involves shifting from product-centric models to customer-centric, data-driven approaches, utilizing technology to deliver hyper-personalized, omnichannel experiences.

To device a better customer strategy, it is important to identify which customer segments to target, come up with value proposition for each customer segment and understand their journey map for better customer engagement.

Digital transformation for customer engagement involves unifying online and offline channels to create seamless, omnichannel experiences, shifting from campaign-centric to customer-centric models. By utilizing Customer Engagement Platforms (CEPs), brands can consolidate data for a 360-degree view, delivering hyper-personalized, consistent interactions across mobile, email, and SMS. For better customer engagement, below are the strategies that are recommended:

- Adopt a Customer Engagement Platform (CEP)

- Segment customers into meaningful personas

- deploy automated self-service options

- Test and iterate to improve the engagement.

## 2.1 Target Customer Segments

| Segment | Profile & Needs | Digital Value Proposition |
| --- | --- | --- |
| B2B OEM Buyers | Large industrial buyers needing custom assemblies, quality certificates, and on-time delivery at scale | Self-service B2B portal: custom configuration, order tracking, digital invoicing, SLA dashboard |
| National Distributors | Channel partners managing inventory, last-mile delivery, and regional demand variation | Distributor portal: real-time stock levels, automated replenishment, performance analytics |
| Export / International Buyers | Overseas clients requiring traceability, quality documentation, and compliance certificates | Blockchain-enabled traceability, digital quality certificates, export compliance automation |
| Internal Operations (Plant Managers) | Need real-time production data, maintenance alerts, and resource utilization insights | IoT dashboards, predictive maintenance alerts, OEE monitoring, shift performance reports |

## 2.2 B2B Customer Journey Map

The following maps the current pain points and proposed digital interventions across the B2B buyer lifecycle:

| Journey Stage | Current Pain Points | Digital Intervention | Expected Improvement |
| --- | --- | --- | --- |
| Awareness & Discovery | No digital presence; word-of-mouth only | SEO-optimised website with product catalogue portal | 3x increase in online inquiries |
| Inquiry & Quoting | Manual emails; 3-5 day quote turnaround; frequent spec errors | AI-assisted CPQ (Configure-Price-Quote) tool | Quote turnaround under 4 hours |
| Order Placement | Phone and email orders; specification errors; no order confirmation | B2B self-service portal with e-signature and validation | 100% digital orders; error rate near zero |
| Production & Tracking | Zero visibility into production status for customers | Real-time order tracking dashboard with exception alerts | Proactive customer notifications; reduced inbound calls |
| Delivery & Fulfilment | Delayed shipments; no ETA accuracy or proactive alerts | GPS logistics integration with automated ETA notifications | On-time delivery improvement of 25% |
| After-Sales & Service | No digital support; reactive complaint-only handling | Ticketing system, remote diagnostics, AI chatbot | NPS improvement of 20+ points |

## 2.3 Value Proposition & Monetization Opportunities

| Opportunity | Description | Revenue Model |
| --- | --- | --- |
| B2B Digital Self-Service Portal | 24/7 ordering, custom configuration, real-time tracking, digital invoicing | Faster deal cycles; lower sales overhead; higher order volume |
| Predictive Maintenance-as-a-Service | IoT-based maintenance monitoring offered to customers who purchase Sahyog equipment | Annual subscription fee: Rs. 2-5 Lakh per client |
| Customization Premium Pricing | Charge a premium for digitally configured, on-demand custom SKUs | 10-15% markup over standard catalogue pricing |
| Data & Analytics Services | Supply chain performance analytics offered to key distributor partners as premium tier | Consultative upsell; tiered partner subscription |
| Export Compliance as a Service | Blockchain-backed traceability and automated compliance documentation for export buyers | Value-added fee for documentation and certification services |

# 3. Operating Model & People

A successful digital transformation change management plan prioritizes employee adoption by aligning leadership, fostering a supportive culture, and providing targeted training. Key actions include communicating the "why" behind the change, appointing change champions, and using frameworks like ADKAR (Awareness, Desire, Knowledge, Ability, Reinforcement) to manage the transition smoothly.

Digital transformation change management differs from traditional change management — it's continuous, with no clear end state. Success depends on three strategies:

- Strategic Communication — keep employees informed and aligned, continuously.

- Continuous Learning — build digital fluency across all departments, not just IT, through ongoing upskilling.

- Center of Excellence (CoE) — a central internal team that leads adoption of new tools and best practices.

Underpinning everything are three pillars: people, technology, and processes — all three must be addressed together. Culture matters too; experimentation and learning from failure are essential mindsets for lasting transformation.

## 3.1 Digital Operating Model

Sahyog will transition to a Product-Aligned, Customer-Centric Operating Model organized around three value streams, governed by a central Digital Office, and delivered by cross-functional agile squads.

DIGITAL STEERING COMMITTEE CEO ¦ COO ¦ CFO ¦ Head of Sales ¦ Head of Operations ¦ Head of IT Monthly Cadence: Prioritization ¦ Budget Reviews ¦ KPI Governance

| VALUE STREAM 1 B2B Sales & Customization | VALUE STREAM 2 Distributor Fulfilment | VALUE STREAM 3 Manufacturing Ops & Service |
| --- | --- | --- |
| Product Owner Tech Lead Process Lead Data Analyst Change Lead | Product Owner Tech Lead Process Lead Data Analyst Change Lead | Product Owner Tech Lead Process Lead Data Analyst Change Lead |

Shared Services (Central Digital Office) Platform & API Integration Layer ¦ Data Lake & Analytics Centre ¦ Cybersecurity & DPDP Compliance ¦ Agile Delivery Practices & Tooling ¦ Vendor & Partner Management

## 3.2 Key New Roles

►  Six critical roles must be in place before major delivery begins. Each row specifies what the role owns and whether it should be filled by external hire, internal promotion, or vendor partnership. Confirm all six roles by end of Q1.

| Role | Responsibility | Hiring / Development Path |
| --- | --- | --- |
| Chief Digital Officer (CDO) | Own the DX strategy, roadmap, and governance; report to CEO | External hire or promoted CTO with DX mandate |
| Digital Transformation PMO Lead | Portfolio management, dependency control, reporting to Steering Committee | Internal promotion from Project Management |
| Data Engineer / Architect | Design and operate the data lake, MDM, and pipeline infrastructure | Hire via campus or lateral; certify on Azure/AWS |
| IoT / OT Engineer | Deploy, manage, and maintain IoT sensors and edge computing at plants | Upskill existing maintenance engineers + hire specialist |
| AI/ML Engineer | Build forecasting, quality, and churn models; maintain MLOps pipeline | Hire from IIT/NIT ecosystem or partner with vendor |
| Change Champions (per plant) | Drive adoption at ground level; surface resistance; feedback to Digital Office | Internal volunteers from each function; trained in Agile and change management |

## 3.3 Change Management Overview

Resistance to change is the #1 leadership obstacle identified in the 2025 State of Smart Manufacturing Report. For Sahyog Industries – a company with 45 years of established working practices – structured change management is not optional; it is the determinant of ROI realization. The change management approach follows a four-phase model:

### Fishbone Analysis: Root Causes of Digital Transformation Resistance

The following Ishikawa (Fishbone) diagram identifies the root causes contributing to the central problem of low digital adoption at Sahyog Industries. Addressing these root causes is the foundation of the change management plan.

| People | Process | Technology | Leadership |
| --- | --- | --- | --- |
| Fear of job displacement by automation Low digital literacy on shop floor Lack of incentives for adoption Generational resistance to new tools | No formal change management methodology Paper-based workflows deeply embedded Lack of standardized SOPs for new systems No feedback loops from operators | Complex legacy system interfaces Poor UX of early digital tools Frequent technical downtime eroding trust Insufficient training on new platforms | No executive sponsor for each initiative DX framed as IT project, not business priority Inconsistent messaging across management levels Short-term performance pressure vs. DX investment |
| ➤ EFFECT: Low digital adoption, ROI shortfall, and failed transformation initiatives |  |  |  |

## 3.4 Change Management Plan

| Phase | Timeline | Key Activities | Success Measures |
| --- | --- | --- | --- |
| 1. Prepare | Weeks 0-8 | Steering Committee sign-off; change impact assessment across all roles and plants; executive sponsor assignment per value stream | Sponsor confirmed; change impact map complete |
| 2. Engage | Weeks 6-16 | Transformation narrative launched via town halls, newsletters, and manager toolkits; recruit 2-3 digital champions per plant and region | 100% site champion coverage achieved |
| 3. Enable | Weeks 10-36 | Role-based training rollout (see Training section); process playbooks on Confluence; on-floor coaches during all pilot go-lives | 80% or more employees trained by end of Q2 |
| 4. Sustain | Months 9-12+ | Weekly adoption metrics tracking; retrospectives every two weeks; feedback loops; incentive program for teams hitting KPI targets | Portal adoption above 70%; support tickets declining trend |

## 3.5 Training Program & Skill Development

Digital transformation is a human-centric process, not just a technological one. Without a trained workforce, technology alone cannot drive transformation

Training programs and skills roadmaps are essential for digital transformation to close widening skills gaps, ensure employees can utilize new technologies, and foster a culture of adaptability. They reduce resistance to change, increase ROI on technology investments, and align employee capabilities with strategic business goals to ensure long-term success.

Training programs help in:

- Bridging the Skills Gap: As technology evolves, organizations face critical skills shortages. A roadmap identifies necessary, future-proof skills—ranging from data analysis to digital literacy—and maps out how to acquire them.

- Maximizing Technology ROI: Expensive new digital tools often go underutilized. Proper training ensures employees can effectively use these systems, driving operational efficiency and preventing wasted investments.

- Reducing Resistance and Improving Adoption: Digital transformation disrupts workflows. Training builds confidence, reduces fear of new technology, and encourages adoption, which is key to overcoming cultural resistance.

- Continuous Learning Culture: A roadmap creates a structured, ongoing process for upskilling, rather than a one-time effort, ensuring the workforce stays current with technological trends.

- Aligning People and Strategy: A roadmap connects business goals with workforce capabilities, ensuring that as technology changes, the staff is empowered to work alongside it.

- Improved Employee Retention: Investing in training shows commitment to employee development, increasing job satisfaction and reducing turnover.

| Audience | Duration | Training Content | Delivery Method |
| --- | --- | --- | --- |
| Executive Leadership | 1 day | DT vision; KPI governance; digital sponsorship responsibilities | Facilitated leadership workshop |
| Managers & Supervisors | 2 days + coaching | Change leadership; dashboard use; performance management with digital tools | Blended: classroom and e-learning |
| Digital Champions | 5 days + project work | Agile methods; data literacy; troubleshooting; train-the-trainer certification | Intensive bootcamp plus ongoing mentoring |
| IT & Data Teams | 10 days + labs | ERP-API integration; ML model lifecycle; cybersecurity practices | Technical labs plus vendor certification tracks |
| Shop Floor Operators | 30-60 min modules | IoT sensor basics; digital work instructions; safety and data hygiene | Mobile-first microlearning (just-in-time) |
| Sales & Distributors | 1 day + portal sandbox | Portal ordering; CPQ configuration; SLA commitments and tracking | Sandbox demo plus hands-on practice sessions |

## 3.6 Skill Development Roadmap

Digital transformation requires not just technology but a workforce that can operate, iterate, and continuously improve it. The skill development roadmap is structured across three levels (Awareness, Practitioner, Expert) and four quarters:

►  Skills are built incrementally — awareness in Q1, practitioner proficiency through Q2–Q3, and expert-level certification in Q4. The Q4 Target column defines the measurable competency standard each domain must reach by year-end. This table drives the quarterly training calendar.

| Skill Domain | Q1 Focus | Q2 Focus | Q3 Focus | Q4 Target |
| --- | --- | --- | --- | --- |
| Digital Leadership | Sponsor training; governance & KPI literacy | Leaders driving portfolio decisions | Advanced DX strategy workshops | All directors at Level 2+ |
| Agile Delivery | Basic Scrum/Agile for squads; backlog management | High-maturity Agile across value streams | Agile coaching certification for champions | All squads self-sufficient |
| Data Literacy | Dashboards; basic analytics for managers | Self-service analytics for decision makers | Advanced analytics for data team | 80% managers using dashboards |
| IoT Operations | Sensor basics; alerts; maintenance workflows | Predictive maintenance models in production | OT security and edge computing | All plant operators Level 1+ |
| AI/ML Fundamentals | Use-case awareness for business users | Model interpretation; output validation | MLOps for data engineers | In-house ML team operational |
| Cybersecurity | Awareness training; data handling rules | Role-based security practices | SIEM operations for IT team | Zero critical incidents in Q4 |

# 4. Technology Architecture & Digital Stack

## 4.1 Strategic Technology Pillars

For Sahyog industries, being a manufacturing company, assets are crucial to keep the business running. Manufacturing is by nature is asset intensive. If Sahyog wants to stay ahead of the competition, focus should be on saving money and run at peak efficiency to optimize the performance of the assets - for which real-time data regarding the performance and condition of the fixed assets is very important.

Sahyog Industries’ digital transformation is anchored on four technology pillars, each addressing a distinct dimension of the business. Prioritization is based on business impact, time-to-value, and feasibility for a mid-market Indian manufacturer.

### Pillar 1: Smart Manufacturing (IoT + AI/ML)

Smart manufacturing transforms Sahyog’s legacy production environment into a proactive, data-driven operation. By embedding IoT sensors across key production lines, the company gains real-time visibility into asset health, energy consumption, and process performance. AI/ML models then convert this data into actionable intelligence – predicting failures before they occur, optimizing scheduling, and recommending quality interventions.

- IoT sensors on CNC machines, conveyors, and assembly lines for real-time condition monitoring

- Manufacturing Execution System (MES) integration with ERP for production-to-order traceability

- AI-powered predictive maintenance reducing unplanned downtime by an estimated 25–35%

- Computer Vision for in-line quality inspection, replacing manual spot-checks

- Digital Twins for simulating production scenarios and capacity planning

### Pillar 2: Supply Chain Visibility & Intelligence

By integrating suppliers, logistics partners, and distributors into a single digital thread, Sahyog gains end-to-end visibility that is currently absent. This reduces the impact of procurement disruptions, improves forecast accuracy, and enables faster response to customer order changes.

- AI-driven demand forecasting integrated with procurement to reduce inventory by 15–20%

- Blockchain-based material traceability from raw material to finished goods for export compliance

- Supplier portal with real-time delivery commitments and exception alerts

- Logistics tracking integration with 3PL providers for last-mile visibility

### Pillar 3: B2B Customer Digital Portal

A digital ordering and engagement portal transforms the customer experience for Sahyog’s B2B buyers and distributors. The portal provides self-service order placement, real-time shipment tracking, invoice management, and customization configuration – reducing order exception rates and cutting order-to-delivery cycle time.

- Configurable product catalogue with custom specifications and digital quoting

- Real-time order status, shipment tracking, and delivery notifications

- Digital invoicing and payment integration (GST-compliant)

- Subscription-based premium analytics for distributors (demand insights, inventory optimization)

### Pillar 4: Data Platform & Analytics

A unified data platform underpins all other pillars. By establishing a governed data lake, master data management framework, and self-service analytics layer, Sahyog enables evidence-based decisions across functions – from production scheduling to sales forecasting to financial planning.

- Cloud-hosted data lake (AWS/Azure) consolidating ERP, IoT, CRM, and supply chain data

- Master Data Management (MDM) eliminating duplicate and inconsistent records

- Power BI or Tableau dashboards for real-time operational KPIs

- ML model pipeline for demand forecasting, quality prediction, and churn risk scoring

## 4.2 Five-Layer Technology Architecture

The Sahyog digital technology stack needs to be organized into five layers, from edge IoT devices at the shop floor through to customer-facing applications, connected by a central integration platform and governed by a unified data and security framework.

All the technologies need work together to create a connected ecosystem where machines and systems communicate, leading to improved decision-making, reduced waste, and enhanced product quality. The integration of these technologies into manufacturing processes is a critical step in achieving digital transformation and maintaining a competitive edge in the market.

## 4.3 Prioritized Technology Use Cases

Below are the technologies that are to be prioritized, being a mid-sized company, Digital Twins and Blockchain are identified as low priority and will be added depending on how effective high priority technology changes are.

| Use Case | Technology Stack | Priority & Phase | Business Impact |
| --- | --- | --- | --- |
| Predictive Maintenance | IoT sensors + Edge AI + ML Models | HIGH - Q1-Q2 | Reduce unplanned downtime by 30-40%; extend equipment life |
| B2B Self-Service Portal | Hybrid Cloud + CRM / ERP API + Web App | HIGH - Q1-Q2 | Faster ordering; reduce manual order handling effort by 60% |
| ERP Implementation | SAP S/4HANA or Oracle NetSuite | HIGH - Q1-Q3 | End-to-end process integration; real-time operational data |
| Demand Forecasting | AI/ML + Data Lake + Time-Series Models | MEDIUM - Q2-Q3 | Reduce inventory holding costs by 20-25%; fewer stockouts |
| Blockchain Traceability | Hyperledger Fabric + Smart Contracts | LOW - Q3 | Export compliance; immutable quality audit trail for buyers |
| Digital Twin | Azure Digital Twins / AWS IoT TwinMaker | LOW - Q3-Q4 | Production simulation; identify inefficiencies; reduce waste 15% |
| Customer & Sales Analytics | Power BI + CRM Data + Customer Portal | MEDIUM - Q2 | Identify upsell opportunities; segment NPS; improve win rates |
| Energy Monitoring | IoT + Edge Analytics + ESG Dashboard | LOW - Q4 | 10% energy cost reduction; readiness for ESG reporting |

## 4.4 Data Privacy & Compliance Framework

| Compliance Area | Measures to Implement |
| --- | --- |
| DPDP Act 2023 (India) | Data consent management system; appoint Data Protection Officer (DPO); data minimization principles; breach notification within 72 hours |
| Data Localization | Customer PII and transactional data stored on India-based cloud regions: AWS ap-south-1 or Azure India Central |
| IT Act 2000 & Amendments | Cybersecurity policy framework; data classification scheme; vendor contracts with mandatory data security clauses |
| ISO 27001 (Target Year 2) | Information Security Management System (ISMS); access controls; AES-256 encryption at rest; TLS 1.3 in transit |
| Export Compliance (Target Year 2) | Blockchain-backed Certificate of Quality and compliance docs; integration with DGFT APIs for trade documentation |

# 5. Roadmap, Delivery & Agile Plan

Sahyog Industries’ digital transformation is governed through a structured three-layer operating model designed to ensure strategic alignment, disciplined execution, and measurable value realization.

The program integrates:

- Strategic Portfolio Governance – via Aha!

- Program Scheduling & Dependency Control – via integrated Gantt framework

- Agile Execution & Delivery Control – via Jira

This architecture ensures full traceability from board-level objectives to sprint-level delivery across the shop floor and enterprise functions.

## 5.1 12-Month Phased Roadmap

|  | Q1 (Months 1-3) FOUNDATIONS | Q2 (Months 4-6) PILOT & VALIDATE | Q3 (Months 7-9) SCALE & EXPAND | Q4 (Months 10-12) OPTIMISE & ROI |
| --- | --- | --- | --- | --- |
| Strategy & Governance | Digital Office setup; Steering Committee formed; skills baseline survey; vendor selection launched | Digital strategy ratified; Q2 backlog groomed; change champions active across all sites | Monthly governance cadence mature; portfolio reviews; mid-year KPI review | Annual DT review complete; Year 2 roadmap approved by Board |
| Technology | ERP vendor signed; cloud infra setup; IoT proof-of-concept on 1 production line; data lake architecture completed | ERP go-live at pilot plant; B2B portal v1 launched; IoT live on 2 lines; basic analytics dashboards | ERP rollout to all plants; predictive maintenance live; demand forecasting model v1; | blockchain proof-of-concept; digital twin proof-of-concept; full analytics suite; energy monitoring live |
| People & Change | Change comms launched; executive briefings done; champions recruited and trained | Core training for all pilot teams; microlearning platform live; feedback loops activated | Training scaled organization-wide; expert certification tracks begin; portal adoption sprint | Certification assessments; competency reviews; Year 2 capability planning complete |
| Key Milestones | Digital Office live; IoT PoC complete; ERP vendor signed | B2B Portal v1 live; ERP pilot go-live; 80% Q2 training complete | Predictive maintenance live; demand forecast v1 deployed; 70% portal adoption | ROI report delivered; blockchain and Digital Twin Proof of Concept; Year 2 roadmap approved |

## 5.2 Detailed Gantt Chart – Workstream Delivery Schedule

The Gantt chart below maps each workstream and initiative across the 12-month program timeline. Shaded cells indicate active delivery periods. Milestones (◆) mark Stage-Gate review points.

| Initiative / Workstream | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 |  | M11 |  | M12 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FOUNDATION & GOVERNANCE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Digital Maturity Assessment & Strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Digital Steering Committee Setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Change Management & Champion Program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Workforce Training Program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cybersecurity & DPDP Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SMART MANUFACTURING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IoT Sensor Deployment (Pilot – Line 1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IoT Rollout (All Production Lines) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MES Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Predictive Maintenance Go-Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AI Quality Inspection (Pilot) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Computer Vision Quality @ Scale |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Digital Twin for Capacity Planning (pilot) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUPPLY CHAIN DIGITIZATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Demand Forecasting AI Model (Build) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AI Demand Forecasting Go-Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Supplier Portal Development & Launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Blockchain Traceability (pilot) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B2B CUSTOMER PORTAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Distributor Portal MVP (Pilot) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ERP-Portal Integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Order Tracking for B2B Buyers Go-Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Customization Options on Portal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Subscription Analytics Launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Full Portal Scale (all distributors) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DATA PLATFORM & ANALYTICS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data Architecture & MDM Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cloud Data Lake Setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| KPI Dashboards (Production, Sales) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ML Pipeline & Model Deployment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Self-Service Analytics Rollout |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DPDP Compliance Audit & Certification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ◆ Stage-Gate Milestones |  |  | ◆ Q1 |  |  | ◆ Q2 |  |  | ◆ Q3 |  |  |  |  | ◆ Q4 |  |

Legend: Colored cells = active delivery period. ◆ = Stage-Gate review (investment unlock decision point). Gantt reflects planned delivery; actual dates subject to Sprint review adjustments.

## 5.2 Resource & Budget Estimate (Year 1)

| Budget Category | Q1 (Rs. L) | Q2 (Rs. L) | Q3 (Rs. L) | Q4 (Rs. L) |
| --- | --- | --- | --- | --- |
| ERP Implementation (License + Consulting) | 30 | 50 | 30 | 10 |
| Cloud Infrastructure & Data Lake Setup | 15 | 10 | 10 | 10 |
| IoT Sensors, Edge Gateways & SCADA Integration | 20 | 15 | 10 | 5 |
| B2B Portal & CRM Development | 10 | 20 | 10 | 5 |
| AI/ML Models & Analytics Platform | 5 | 10 | 15 | 10 |
| Blockchain Proof-of-Concept & Deployment | 0 | 5 | 15 | 10 |
| Training, Change Management & HR Programs | 5 | 10 | 10 | 5 |
| Cybersecurity, Compliance & DPDP Readiness | 5 | 5 | 5 | 5 |
| TOTAL (Rs. Lakhs) | 90 | 125 | 105 | 60 |

Total Year 1 Investment Rs. 3.80 Crore (implementation costs) + Rs. 0.40 Crore (10% contingency buffer) = Rs. 4.20 Crore total ¦ Headcount: 1 DT Programme Director + 3 Value Stream Leads + 6 Agile Team Members (mix of internal redeployment and new hires)

### Opex vs Capex Split (Year-1)

| Type | Approx % |
| --- | --- |
| Capex (Hardware, Platforms) | 55% |
| Opex (Licenses, Cloud, People) | 45% |
| TOTAL (Rs. Lakhs) | 90 |

# 6. Metrics, KPIs & ROI Analysis

## 6.1 KPI Map Tied to Business Goals

| Domain | KPI | Baseline | Target (12M) | Measurement Source |
| --- | --- | --- | --- | --- |
| Operations | Overall Equipment Effectiveness (OEE) | 52% | 68% | IoT + MES Dashboard |
| Operations | Unplanned Downtime (hrs/month) | 48 hrs | Under 20 hrs | Predictive Maintenance Log |
| Operations | Production Defect Rate | 3.2% | Under 1.5% | MES Quality Reports |
| Supply Chain | On-Time In-Full (OTIF) Delivery | 68% | 88% | ERP and WMS Reports |
| Supply Chain | Inventory Holding Days | 45 days | 28 days | ERP Inventory Module |
| Supply Chain | Supplier Lead Time (avg days) | 18 days | 10 days | Procurement Portal |
| Customer | B2B Portal Adoption Rate | 0% | 70% | Portal Analytics Dashboard |
| Customer | Net Promoter Score (NPS) | 32 | 52 | Quarterly Customer Survey |
| Customer | Quote-to-Order Cycle Time | 4 days | Under 4 hours | CRM / CPQ Reports |
| Revenue | Revenue from Digital Channels | 0% | 20% of total revenue | CRM Revenue Tracking |
| People | Employee Training Completion | N/A | 80% or above | LMS / HR Information System |
| Compliance | DPDP Act Compliance Score | 0% | 100% | Quarterly Compliance Audit |

## 6.2 ROI & NPV Calculation (Year 1)

The following financial model uses conservative assumptions for a mid-market Indian manufacturer. All figures are in Indian Rupees (Crore). Investment costs are capitalized; benefits are measured from Month 4 onwards as systems reach production stability

| Value Driver | Annual Benefit (Rs.) | Basis of Estimation |
| --- | --- | --- |
| Reduced unplanned downtime (30% reduction) | 0.80 Cr | Avg. downtime cost approx Rs. 2.6 Cr/yr x 30% improvement |
| Inventory holding cost reduction (40% reduction) | 0.60 Cr | Current inventory holding cost approx Rs. 1.5 Cr/yr x 40% |
| Revenue uplift from digital channels / portal | 0.90 Cr | 5% incremental revenue on Rs. 18 Cr annual base revenue |
| Labour cost savings through process automation | 0.40 Cr | 20 FTEs reallocated to higher-value tasks; Rs. 2L saving per FTE |
| Predictive vs. reactive maintenance savings | 0.45 Cr | Industry benchmark: Rs. 1.5 Cr current maintenance spend x 30% |
| Supply chain OTIF improvement (penalty reduction) | 0.25 Cr | Customer retention value plus SLA penalty avoidance |
| TOTAL GROSS BENEFIT (Year 1) | Rs. 3.40 Cr | 50% realization assumed in Year 1 due to go-live timelines |

| Financial Metric | Year 1 | Year 2 (Projected) |
| --- | --- | --- |
| Total Investment | Rs. 4.20 Cr | Rs. 2.50 Cr (sustain and scale costs) |
| Total Gross Benefit | Rs. 3.40 Cr (50% realization) | Rs. 6.80 Cr (full realization) |
| Net Benefit | - Rs. 0.80 Cr | + Rs. 4.30 Cr |
| Cumulative NPV at 10% discount rate | - Rs. 0.73 Cr | + Rs. 3.57 Cr (cumulative) |
| Return on Investment (ROI) | -19% (investment phase) | ~172% standalone Year 2 |
| Payback Period | ~18 months | Break-even by Q2 of Year 2 |

ROI Summary Note Year 1 shows a negative ROI as it is primarily an investment and implementation year with partial benefit realization. Positive cumulative ROI begins in Q2 of Year 2. Over a 3-year horizon, NPV at 10% discount rate is positive Rs. 7.2 Crore, confirming strong long-term strategic and financial value of the transformation program.

# 7. Risk, Security & Regulatory Framework

When Sahyog Industries, embarks on a digital transformation (DX), it faces a wide spectrum of risks—strategic, operational, technological, legal & compliance, financial, and people/culture related. Below is a comprehensive risk analysis along with associated compliances, risk mitigation plans, and contingency milestones.

## 7.1 Risk Register

For smooth transition, risks are to be identified, and mitigation strategy needs to be devised. Below table outlines the identified risks and their mitigation strategy.

| # | Risk Description | Category | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| 1 | ERP implementation overrun in time and cost | Technical | High | High | - Fixed-price contracts - Phased rollout approach - PMO oversight - 10% contingency budget held in reserve |
| 2 | Employee resistance to digital adoption | People | High | High | - Structured change management plan - change champions program - executive sponsorship - incentive alignment from Day 1 |
| 3 | Cybersecurity breach post-digitization | Security | Medium | Critical | - ISO 27001 roadmap; quarterly VAPT - Zero Trust network architecture - documented incident response plan and drills |
| 4 | DPDP Act non-compliance | Compliance | Medium | High | - Appoint DPO - consent management system - data audit - engage legal counsel for ongoing guidance |
| 5 | IoT device failures or sensor data inaccuracy | Technical | Medium | Medium | - Vendor SLAs - redundant sensors at critical points - edge-level validation rules - regular calibration schedule |
| 6 | Supply chain data integration failures | Operational | Medium | High | - API testing protocols - fallback manual processes documented - supplier onboarding and technical support program |
| 7 | Key digital talent attrition | People | Medium | Medium | - Competitive compensation benchmarking - skills development investment - internal mobility pathways - succession plans |
| 8 | Budget overrun due to scope creep | Financial | High | Medium | - Strict change control board - MoSCoW prioritization - monthly budget reviews at Steering Committee level |
| 9 | Cloud or technology vendor lock-in | Strategic | Low | High | - Multi-cloud strategy design - open API standards - contract exit clauses - in-house skill development to reduce dependency |
| 10 | Poor internet connectivity at remote plant locations | Operational | Medium | High | - Hybrid edge-cloud architecture - offline-first IoT design - backup LTE/4G connectivity with automatic failover |
| 11 | Data / Cyber security issues | Operational | Medium | High | - Stringent network security - Role based access - Data security; encryption at rest and in transit - OT / IoT Security |

## 7.3 Contingency Milestones

| Trigger Condition | Contingency Action | Decision Owner |
| --- | --- | --- |
| ERP delay exceeds 4 weeks | Activate parallel manual processes; escalate to Steering Committee; invoke vendor SLA penalty clause; reassess scope | COO and Programme Director |
| B2B portal adoption under 30% by end of Q2 | Intensify change management; simplify UX based on user feedback; executive mandate; activate incentive program | Head of Sales and Change Lead |
| Cybersecurity incident of any severity | Activate IR plan immediately; isolate affected systems; notify Board within 4 hours; CERT-In notification within 6 hours | CISO and Legal Counsel |
| Budget overspend exceeds 15% of approved | Freeze non-critical discretionary spend; descope lower-priority Q4 items; reforecast with CFO approval | CFO and Steering Committee |
| Key technology vendor failure | Activate backup vendor shortlist maintained from Q1 RFP; bridge with interim manual processes while transition occurs | Head of IT and Programme Director |

## 7.4 Three-Layer Transformation Governance

The programme is governed through a three-layer operating model ensuring full traceability from Board-level objectives to sprint-level delivery:

►  The three layers are intentionally separate so that strategic decisions (Layer 1) are not slowed by day-to-day delivery concerns (Layer 3). Information flows upward weekly from Jira sprint reports → monthly Gantt PMO reviews → quarterly Aha! steering presentations.

| Layer | Purpose | Key Capability | Tool / Cadence |
| --- | --- | --- | --- |
| Strategic Portfolio (Layer 1) | Ensure DX initiatives are aligned to enterprise strategy and measurable outcomes | Vision & goal definition; initiative prioritization (value/effort/risk); KPI mapping; ROI tracking | Aha! – Quarterly roadmap review by Steering Committee |
| Program Execution (Layer 2) | Translate strategy into sequenced, cross-functional plans with dependencies and milestones | Workstream planning; critical path management; resource alignment; milestone governance | Gantt Framework (Excel/MS Project) – Monthly PMO review |
| Agile Delivery (Layer 3) | Enable sprint-based, transparent, measurable delivery of digital capabilities | Sprint planning; backlog management; daily standups; velocity tracking; retrospectives | Jira – Fortnightly sprint reviews |

# 8. Aha! Strategic Roadmap – Portfolio View

The Aha! roadmap is the single source of strategic truth for the Digital Transformation Program. While the Gantt chart (Section 5) shows delivery scheduling at the workstream level, the Aha! roadmap operates one level higher — showing how each initiative maps to a strategic goal, which value stream owns it, what its business priority is, and how it contributes to the overall program vision.

The Aha! roadmap is reviewed by the Digital Steering Committee every quarter. Initiatives can be re-prioritized between quarters based on business outcomes, but the strategic goals remain fixed for the 12-month cycle. The roadmap below replicates the Aha! structure across the four strategic release themes.

## 8.1 Program Vision & Strategic Goals

►  The programme vision is decomposed into five measurable strategic goals. Every initiative on the Aha! roadmap must link to at least one of these goals. Initiatives that cannot be mapped to a goal are de-prioritized or removed from the backlog.

| # | Strategic Goal | Outcome Statement | Primary KPI |
| --- | --- | --- | --- |
| G1 | Operational Excellence | Reduce unplanned downtime and defect rate across all production lines | OEE +15%; Unplanned Downtime −25% |
| G2 | Supply Chain Resilience | Achieve end-to-end supply chain visibility and reduce lead times | Forecast Accuracy >85%; Supplier OTD >90% |
| G3 | Customer Centricity | Deliver a best-in-class B2B digital experience for buyers and distributors | Portal Adoption >70%; NPS >50; Order Cycle −20% |
| G4 | Data & Intelligence | Build a single source of truth enabling data-driven decisions at every level | 80% managers using live dashboards by Q4 |
| G5 | Talent & Culture | Build a digitally capable workforce that can operate and improve the platform | 80% employees trained; Digital tool usage >75% |

## 8.2 Aha! Initiative Roadmap by Release Theme

►  Each row is one initiative on the Aha! board. Columns show the owning value stream, business priority (P1–P3), the linked strategic goal, the target release quarter, and current status. This is the view the Digital Steering Committee reviews monthly to track portfolio health and adjust priorities.

| Initiative Name | Value Stream | Priority | Goal | Release | Status | Success Metric |
| --- | --- | --- | --- | --- | --- | --- |
| RELEASE THEME 1 – Foundation & Discovery (Q1: Months 1–3) |  |  |  |  |  |  |
| Digital Maturity Assessment & Baseline | Digital Office | P1 | G1–G5 | Q1 M2 | ✓ Complete | Maturity baseline report approved by Steering Committee |
| Digital Steering Committee & Governance Setup | Digital Office | P1 | G1–G5 | Q1 M1 | ✓ Complete | First Steering Committee meeting held |
| Change Champion Recruitment & Onboarding | All Streams | P1 | G5 | Q1 M3 | ✓ Complete | 2–3 champions per plant confirmed |
| Distributor Portal – MVP (Pilot: Top 20 Distributors) | Distributor | P1 | G3 | Q1 M3 | ✓ Complete | MVP live; 10+ distributors placing orders |
| Production KPI Dashboards (Quick Win) | Manufacturing | P2 | G1 | Q1 M3 | ✓ Complete | Dashboards live for plant managers |
| Cybersecurity Zero Trust Framework Design | Digital Office | P1 | G1–G4 | Q1 M3 | ⏳ In Progress | Security architecture signed off |
| RELEASE THEME 2 – Technology Enablement (Q2: Months 4–6) |  |  |  |  |  |  |
| ERP – Distributor Portal Integration | Distributor | P1 | G3 | Q2 M5 | ⏳ In Progress | ERP sync live; order exceptions <5% |
| IoT Sensor Deployment – Pilot Line 1 | Manufacturing | P1 | G1 | Q2 M4 | ⏳ In Progress | Real-time telemetry from Line 1 confirmed |
| AI/ML Demand Forecasting – Model Build | Supply Chain | P1 | G2 | Q2 M6 | ○ Planned | Forecast MAPE <15% on test data |
| B2B Order Tracking Go-Live | B2B Sales | P1 | G3 | Q2 M5 | ○ Planned | 100% orders tracked; buyer CSAT >4.0/5 |
| Core Workforce Training – Wave 1 | Digital Office | P1 | G5 | Q2 M4–6 | ⏳ In Progress | 50% of target employees trained |
| MES Implementation (Phase 1) | Manufacturing | P2 | G1 | Q2 M4–6 | ○ Planned | MES live on 2 production lines |
| Cloud Data Lake Architecture Setup | Digital Office | P2 | G4 | Q2 M5 | ○ Planned | Data lake ingesting ERP + IoT data |
| RELEASE THEME 3 – Scaling & Optimization (Q3: Months 7–9) |  |  |  |  |  |  |
| IoT Rollout – All Production Lines | Manufacturing | P1 | G1 | Q3 M7 | ○ Planned | All key lines instrumented; OEE dashboard live |
| Predictive Maintenance Go-Live | Manufacturing | P1 | G1 | Q3 M8 | ○ Planned | First ML-triggered maintenance action executed |
| AI Demand Forecasting Go-Live | Supply Chain | P1 | G2 | Q3 M7 | ○ Planned | Forecast accuracy >85%; procurement aligned |
| Supplier Portal Launch | Supply Chain | P2 | G2 | Q3 M8 | ○ Planned | Top 15 suppliers onboarded |
| Portal Customization Options Launch | B2B Sales | P1 | G3 | Q3 M8 | ○ Planned | Customization orders >10% of portal volume |
| Subscription Analytics Model Launch | Distributor | P2 | G3 | Q3 M9 | ○ Planned | 5+ distributors on paid analytics tier |
| KPI Dashboards – Production & Sales | Digital Office | P1 | G4 | Q3 M7 | ○ Planned | All managers accessing dashboards weekly |
| AI Quality Inspection Pilot | Manufacturing | P2 | G1 | Q3 M9 | ○ Planned | Defect detection rate >90% on pilot line |
| RELEASE THEME 4 – Advanced Capabilities & Scale (Q4: Months 10–12) |  |  |  |  |  |  |
| Computer Vision Quality @ Scale | Manufacturing | P1 | G1 | Q4 M10 | ○ Planned | CV deployed on 3+ lines; defect rate −30% |
| Blockchain Traceability – Proof of concept | Supply Chain | P2 | G2 | Q4 M11 | ○ Planned | Export batch traceability live; |
| Full Data Lake + ML Pipeline | Digital Office | P1 | G4 | Q4 M10 | ○ Planned | All 4 data domains feeding ML models |
| Self-Service Analytics Rollout | Digital Office | P1 | G4 | Q4 M11 | ○ Planned | 80% managers using self-service BI |
| Digital Twin for Capacity Planning (pilot) | Manufacturing | P3 | G1 | Q4 M12 | ○ Planned | Digital twin model validated against actual output |
| Full Portal Scale (All Distributors) | Distributor | P1 | G3 | Q4 M10 | ○ Planned | Portal adoption >80% of distributor network |
| DPDP Compliance Audit & Certification | Digital Office | P1 | G4–G5 | Q4 M12 | ○ Planned | Zero non-conformances in external audit |
| Year-1 Retrospective & Year-2 Roadmap | Digital Office | P1 | G1–G5 | Q4 M12 | ○ Planned | Year-2 Aha! roadmap approved by Board |
| Priority: P1 = Must Have (this quarter) P2 = Should Have (high value, some flexibility) P3 = Nice to Have (defer if resource-constrained) Status: ✓ Complete ⏳ In Progress ○ Planned |  |  |  |  |  |  |

## 8.3 Backlog Management & Prioritization Rules

The Aha! backlog is governed by the following rules to prevent scope creep and maintain delivery focus:

- Any new initiative requested mid-quarter must be scored against the existing P1 backlog before being added — something must be de-prioritized or deferred to accommodate it.

- P1 items must not exceed 70% of squad capacity per quarter; the remaining 30% is held for defect resolution, technical debt, and unplanned support.

- The Digital Steering Committee reviews and adjusts the backlog at the start of each quarter during the Quarterly Business Review (QBR).

- Initiatives moved out of a quarter must be re-scored in the next quarter — they do not automatically carry forward with the same priority.

- All changes to the Aha! roadmap require sign-off from the CDO and the relevant value stream’s Product Owner.

# Appendix A: Maturity Level Descriptors

| Level | Stage Name | Characteristics |
| --- | --- | --- |
| 1 | Initial | Entirely manual and paper-based workflows; siloed departments; no IT systems integration; fully reactive decision-making; no KPI tracking |
| 2 | Emerging | Basic digitization in isolated areas (e.g. Excel spreadsheets); limited inter-departmental data sharing; pilot digital projects exist but are disconnected |
| 3 | Defined | Standardized digital processes across key functions; ERP and CRM are implemented; defined data governance policies; proactive analytics starting to emerge |
| 4 | Integrated | Fully connected systems with real-time data flow; cross-functional collaboration enabled by data; KPI-driven culture; data-informed decision making at all levels |
| 5 | Optimized | AI and ML-driven autonomous optimization; self-learning and predictive systems; fully automated operations; digital-first culture embedded across the organization |

# Appendix B: Key Assumptions & Data Sources

| # | Assumption / Source / Method |
| --- | --- |
| A1 | Sahyog Industries annual revenue is assumed to be approximately Rs. 18 Crore, consistent with a mid-sized Indian component manufacturer with national distribution |
| A2 | Current digital maturity assessed as Level 2 (Emerging) based on pain points in capstone brief: legacy facilities, no integrated ERP, manual and siloed processes |
| A3 | Benefit estimates are based on industry benchmarks from McKinsey Global Institute (Industry 4.0 in Manufacturing, 2022) and Gartner IoT manufacturing research reports |
| A4 | ERP implementation timeline and costs are based on typical SAP S/4HANA and Oracle NetSuite mid-market deployments in Indian manufacturing (Nasscom Industry Report, 2023) |
| A5 | NPV calculated at a 10% discount rate over a 3-year horizon. Year 1 benefits are 50% realised due to implementation and go-live timelines within the year |
| A6 | Workforce estimated at 500-800 employees based on profile of a 45-year-old mid-sized manufacturer; training costs and headcount scaled accordingly |
| A7 | Digital Maturity Framework adapted from the European Digital Innovation Hub Open DMAT tool (european-digital-innovation-hubs.ec.europa.eu/open-dma) |
| A8 | All financial estimates are in Indian Rupees at 2025 market rates. No currency hedging has been assumed in export revenue calculations for Year 1 |

# Appendix C: Participation Matrix

| Team Member | Role | Key Contributions |
| --- | --- | --- |
| Member 1 | DT Strategy Lead | Section 1: Strategic alignment, SWOT analysis, digital maturity assessment |
| Member 2 | Customer & Market Lead | Section 2: Customer segments, journey mapping, monetization opportunities |
| Member 3 | Technology Architect | Section 4: Technology architecture, use cases, compliance framework |
| Member 4 | People & Change Lead | Section 3: Operating model, change management plan, training and skills roadmap |
| Member 5 | Programme Manager | Section 5: 12-month roadmap, agile plan, resource and budget estimates |
| Member 6 | Finance & Risk Analyst | Sections 6 and 7: KPI map, ROI and NPV calculations, risk register, security framework |

Sahyog Industries Digital Transformation Roadmap  |  Confidential  |  Accredian Capstone Project 2025  |  All rights reserved